## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-SP-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1476 |  |  | Transmital Date: 10/10/2022
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1476 |  |  | Transmital Date: 10/10/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در كلاسهاي CN05 و CN07 و FN05 و FN07 و CS00 و FS00 درجه حرارت طراحي بر اساس دماي خروجي كمپرسور و كولر هوايي اصلاح گردند. در صفحه 14 بخش 7.2 جدول 1 و جداول بخش 8 اصلاحات لازم اعمال گردد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | - اعمال گردید. |  |  | Closed
2 | در جداول بخش 8 سرويس هاي ذكر شده در كلاسهاي مختلف با جدول 1 در بخش 7.2 مطابق باشد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | - اعمال گردید. |  |  | Closed
3 | در كلاس FN07 كد طراحي به ASME B31.3 اصلاح گردد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | با توجه به كامنت ارائه شده در مدرك Wall Thickness Calculation Report در صورت هرگونه تغيير ضخامت لوله در مدرك PMS لحاظ گردد.. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: