## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0732 |  |  | Transmital Date: 14-Mar-2022
Document Title: Rough Grading Plans -W028 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-0732 |  |  | Transmital Date: 14-Mar-2022
[5 empty] | CRS No: NISOC-CRS-BK-W028-PEDCO-110-CV-DW-0001_D02 |  |  | CRS Status:
عطف به نامه های شماره 01/2294/46725 و 02/2294/897925 تغییراتی که منجر به تغییر این مدرک نیز گردید اعمال شده است.
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فایل اتوکد مدرک توپوگرافی قابل مشاهده نیست. مقتضی است با نسخه 2013 تهیه و ارسال گردد. |  | 1401/2294/6027 | 1401/01/10 | اعمال گردید.
2 | تمامی کانال‌های کنترل سیلاب با یک نام در مدارک لحاظ شوند. |  | 1401/2294/6027 | 1401/01/10 | اعمال گردید. نام تمامی کانال‌ها به Flood control channel تغییر یافت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: