## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0005_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2249 |  |  | Transmital Date: 8/9/2023
Document Title: Chemical Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2249 |  |  | Transmital Date: 8/9/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D03 |  |  | CRS Status: CR3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به پیشنهاد سازنده و در نتیجه ظرفیت بسیار پایین محاسبه شده برای پمپ های تزریق نسبت به ظرفیت محاسبه شده طبق تجربه پیمانکار پروژه (که منبع داده های آن نیز مشخص نمی باشد) شش برابر شده است مقتضی است تا امکان کارایی موثر پمپ های تزریق در این بازه وسیع بررسی گردد و نتیجه به کارفرما جهت تصمیم گیری اعلام گردد. شایان ذکر است که با توجه به تجربه کارفرما در نظر گرفتن ظرفیت های غیر واقعی و اغلب بیشتر لز میزان لازم صرفا منجر به بلا استفاده شدن سیستم تزریق مواد شیمیایی و در نتیجه بلا استفاده شدن سیستم تزریق مواد شیمیایی و در نتیجه متضرر گردیدن کل واحد در مسالع خوردگی می گردد. علی ای حال با توجه به وضعیت کنونی پروژه و جلوگیری تاخیرات بیش از این، این امور آمادگی لازم جهت برگزاری جلسه و جمع بندی و نهایی سازی موضوع را دارد. |  | 1402/2294/282315 | 1402/07/18 | مطابق با صورتجلسه 14020724 مورخ 1402.07.24 اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021