## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1468 |  |  | Transmital Date: 10/9/2022
Document Title: F&G Location Layout For Process Area |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1468 |  |  | Transmital Date: 10/9/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG- INS-01-05933 | 2022-10-19 | ملاحظه گردید
2 | Tag ها ناخوانا هستند براي مثال نقشه صفحه 6 . موارد مجددا بررسي و اصلاح گردد. |  | BK-SUR-ENG- INS-01-05933 | 2022-10-19 | مدرک اصلاح گردید
3 | با توجه به كامنت پيشين، فاصله نصب ديتكتورها بر اساس پوشش دهي آن ها مشخص گردد. |  | BK-SUR-ENG- INS-01-05933 | 2022-10-19 | همه FD ها حداقل فاصله 20 متر را پوشش می دهند و در مدرک نشان داده شد
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: