## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-SU-DW-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1709 |  |  | Transmital Date: 19-DEC-2022
Document Title: Plan & Profile Drawings For Gas Pipeline (to Siahmakan) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1709 |  |  | Transmital Date: 19-DEC-2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-SU-DW-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقشه مسیر پیشنهادی خط لوله گاز از بینک به سیاهمکان قبلا با شماره نقشه A79114 در اسناد پیمان گنجانده شده است لذا نیازی به تهیه نقشه جدید توسط پیمانکار نبوده است. از اینرو در مسیر پیشنهادی پیمانکار محل اتصال به ایستگاه تقویت فشار بینک، با نقشه مذکور اختلاف دارد. لذا ضروری است تا مختصات دقیق UTM محل اتصال در بینک را جهت اصلاح نقشه A79114 (در صورت لزوم) اعلام نمایید. |  | 1402/2294/11625 | 1402/01/16 | مختصات دقیق UTM محل اتصال جدید به شرح زیر تقدیم می گردد (در نقشه نیز نشان داده شده است).
Easting= 437323.474
Northing=3289936.663
UTM-WGS1984-ZONE 39 N
2 | مجددا تاکید می گردد از آنجا که نقشه های مندرج در اسناد پیمان توسط کارفرما تهیه گردیده، ضروری است تا پیمانکار تغییر/عدم تغییر پروفایل مسیر ارسال شده را نسبت به نقشه های اسناد پیمان اعلام نموده و در صورت وجود تغییرات، موقعیت مکانی و علل تغییرات بر روی نقشه پیشنهادی جهت بررسی، مشخص گردد. |  | 1402/2294/11625 | 1402/01/16 | همانطور که در ویرایش قبلی اشاره شد تنها تغییر در پلان-پروفایل مسیر ارسال شده، مربوط به نقطه اتصال به ایستگاه تقویت فشار بینک بود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: