## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2154 |  |  | Transmital Date: 5/29/2023
Document Title: Data Sheets For Flow Transmitter/Diff. Pressure Transmitter - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2154 |  |  | Transmital Date: 5/29/2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-DT-0007_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-02-07858 | 2023-06-12 | ملاحظه گردید.
2 | با توجه به اينكه مدارك پيش نياز اين مدرك نهايي نشده است، در صورت هر گونه تغيير در اين مدرك نيز بايد منعكس گردد. نهايي شدن شدن اين مدرك منوط به نهايي شدن مدارك پيش نياز مي باشد. |  | BK-SUR-ENG-INS-02-07858 | 2023-06-12 | ملاحظه گردید.
3 | بازگشت به كامنت ارائه شده در مدرك پيشين با توجه به اينكه مدرك DS براي FE هنوز ارائه نشده است و در اين مدرك نيز محاسباني ارائه نشده است رنج هاي در نظر گرفته شده در اين مدرك قابل بررسي نمي باشد. |  | BK-SUR-ENG-INS-02-07858 | 2023-06-12 | با توجه به مدرک Specification For Instrumentation قسمت 9.1 و همچنین مهندسی صورت گرفته اختلاف فشار برای طراحی اوریفیس و FT ها رنج های مشخصی است که در این پروژه معادل 250 میلی بار در نظر گرفته شده است. این روال در طراحی ایستگاه فشار گاز نیز طی شده است و قطعا دیتا شیت FE نیز با همین فرض تهیه و ارسال میشود.
4 | بازگشت به كامنت ارائه شده در مدرك پيشين در خصوص انتخاب رنج FT شفاف سازي گردد. |  | BK-SUR-ENG-INS-02-07858 | 2023-06-12
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: