## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-CN-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1574 |  |  | Transmital Date: 11/5/2022
Document Title:Calculation book for (CV,PSV,Pump & Line sizing) - Extension of Binak BC Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1574 |  |  | Transmital Date: 11/5/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-CN-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محاسبات شیرهای کنترلی: عدد فشار بخار اصلاح شود. |  | BK-SUR-ENG-PCS-01-06217 | 2022-11-20 | اعمال گردید.
2 | محاسبات پمپ: نظری مطرح نمی باشد. |  | BK-SUR-ENG-PCS-01-06217 | 2022-11-20 | مورد تایید است.
3 | محاسبات خطوط: نظری مطرح نمی باشد. |  | BK-SUR-ENG-PCS-01-06217 | 2022-11-20 | مورد تایید است.
4 | محاسبات شیرهای ایمنی: نظری مطرح نمی باشد. پیشنهاد می گردد شیرهای ایمنی برای خطوط لوله جریانی با جریانهای متفاوت، بر اساس بزرگترین سایز و به صورت یکسان، انتخاب شوند. |  | BK-SUR-ENG-PCS-01-06217 | 2022-11-20 | مورد تایید است.
5 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06217 | 2022-11-20 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: