## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-IN-SP-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0485 |  |  | Transmital Date: 1/22/2022
Document Title: Specification For LBV |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-0485 |  |  | Transmital Date: 1/22/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0013_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ به Reply Sheet : موارد 1 و 2 و 3 و 4 و 5 و 6 نظر خاصی مطرح نمی باشد. |  | 1400/2294/443274 | 1400/12/19 | نظر کارفرمای محترم ملاحظه گردید.
2 | موارد مربوط به گارانتی ، آموزش ، خدمات پس از فروش و ... که برای سازنده تعهدآور است میبایست مورد تایید سازنده قرار گیرد. |  | 1400/2294/443274 | 1400/12/19 | موارد ذکر شده به تایید سازنده خواهد رسید.
3 | در قسمت scope هر گونه تغییرات یا اختلاف در مشخصات در هر مقطع از پروژه باید به تایید client برسد. |  | 1400/2294/443274 | 1400/12/19 | نظر کارفرمای محترم ملاحظه گردید.
4 | کلاس v برای seat leakage کافی نمی باشد. |  | 1400/2294/443274 | 1400/12/19 | با توجه به نظر کارفرمای محترم کلاس VI در نظر گرفته شد.
.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: