## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0016 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2362 |  |  | Transmital Date: 9/12/2023
Document Title: Structural Drawing For Close Drain Sump Pit (SU-2201 A) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2362 |  |  | Transmital Date: 9/12/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0016_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-281723 | 1402/07/18 | عرض واتراستاپ به 30 سانتیمتر تغییر یافت
2 |  |  | 1402-2294-281723 | 1402/07/18 | به استاندارد STANDARD DRAWING FOR HANDRAIL با شماره STANDARD DRAWING FOR HANDRAIL اشاره شده است
3 |  |  | 1402-2294-281723 | 1402/07/18 | مدارک مکانیکال دیتا شیت به لیست اضافه شد
4 |  |  | 1402-2294-281723 | 1402/07/18 | لیستوفر تهیه و به نقشه ها اضافه گردید
5 |  |  | 1402-2294-281723 | 1402/07/18 | بازشو دیوار WALL04 اضافه گردید
6 |  |  | 1402-2294-281723 | 1402/07/18 | مختصات واحد های مربوط به ایستگاه کمپرسور گاز به صورت محلی در نظر گرفته می شود
7 |  |  | 1402-2294-281723 | 1402/07/18 | مشخصات فنی پوشش امولوسیونی به ردیف 14 نوت نقشه ها اضافه شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: