## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-BD-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1764 |  |  | Transmital Date:1/4/2023
Document Title: ESD Block Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1764 |  |  | Transmital Date:1/4/2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-BD-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علت حذف Request from existing ESD system از ESD0 نسبت به ویرایش پیشین چه می باشد؟ در صورت که علتی باعث توقف اضطرار کل کارخانه گردد می بایست تاسیسات جدید نیز متوقف گردد. |  | 1401-2294-471072 | 1401/12/09 | کامنت فوق اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: