## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PH-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1748 |  |  | Transmital Date: 01/01/2023
Document Title: Control Philosophy |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1748 |  |  | Transmital Date: 01/01/2023
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-PH-0002-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 5 مدرک، نام پکیج ها و نوع آن ها به صورت کامل درج گردد. (به عنوان نمونه بسنه نم زدا نوع B و...) |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
2 | در بخش 5 مدرک به ارتباط بین DCS واحد قدیم و جدید اشاره گردد. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
3 | در صفحه 11 مدرک در پاراگراف سوم مشخص شود که پس از تایید Fire و Gas در سیستم F&G، قطع اضطراری از طریق سیستم ESD اعمال می شود. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
4 | در صفحه 11 مدرک در انتهای خط اول پاراگراف چهارم پس از عبارت By Package Vendor نوشته شود By client approval. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
5 | در صفحه 12 بخش 7 به Interface بین سیستم F&G و FACP،HVAC و CO2 PK اشاره گردد. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
6 | در صفحه 12 بخش 8 به ارتباط سیستم ESD واحد موجود و جدید اشاره شود. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
7 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06693 | 2023-01-01 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 17/01/2023 |  |  |  |  | Date: