## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-BD-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1764 |  |  | Transmital Date:1/4/2023
Document Title: ESD Block Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1764 |  |  | Transmital Date:1/4/2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-BD-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به وجود مغایرتهایی میان این مدرک و مدرک ESD Level Hierarchy، ضروریست این مدارک یکسان سازی شوند. |  | BK-SUR-ENG-PCS-01-06702 | 2023-01-18 | اصلاح گردید.
2 | Cause مربوط به ESD-0 سیستم موجود، در مدرک نشان داده شود. |  | BK-SUR-ENG-PCS-01-06702 | 2023-01-18 | اعمال گردید.
3 | ESD-1 برای هر خط لوله جریانی به صورت مستقل در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-06702 | 2023-01-18 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: