## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0012 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2362 |  |  | Transmital Date: 9/12/2023
Document Title: Calculation Note for Close Drain Sump Pit (SU-2201 A) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2362 |  |  | Transmital Date: 9/12/2023
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-ST-CN-0012_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-281723 | 1402/07/18 | در صفحه 12 دفترچه محاسبات ذکر گردیده است که مطابق با نشریه ی 038 سیستم ستون طره ای در نظر گرفته شده است .
2 |  |  | 1402-2294-281723 | 1402/07/18 | مورد تایید است .
3 |  |  | 1402-2294-281723 | 1402/07/18 | کنترل های مربوط به فنداسیون در صفحه 18 دفترچه محاسبات نمایش داده شده است همچنین جدول مربوط به خروجی های حاصل از نرم افزار مربوط به نشست زیر فنداسیون محاسبه تنش زیر فنداسیونو مقایسه با میزان تنش قابل قبول و ... در ادامه ارائه گردیده است. محاسبات مربوط به بالازدگی هم با توجه به ابعاد سازه در صفحه آخر دفترچه محاسبات اورده شده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: