## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PI-DG-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1617 |  |  | Transmital Date: 11/27/2022
Document Title: Material Flow Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1617 |  |  | Transmital Date: 11/27/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PI-DG-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Material comments will be finalized after updating corrosion study and Material Selection based on mentioned comments sent by Email BK-SUR-ENG-PIP-01-03917 dated 4/16/2022. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Updated "Corrosion Study and Material Selection" has been submitted. |  |  | See Item 6
2 | Material Flow Diagrams shall be in accordance with final P&ID's by identifying size and rating of all Valves, reducers and Equipment (if any). It is better to identify all Instruments, too. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | This document is revised based on last revision of PFD. |  |  | See Item 7
3 | The document Piping corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PI-RT-0001 shall be referred. The title shall be revised from Pipeline to Piping. The document Pipeline corrosion study and Material Selection Report BK-SSGRL-PEDCO-110-PL-RT-0001 and BK-PPL-PEDCO-320-PI-RT-0001 shall be referred, too |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Noted. |  |  | Closed
4 | Note 1 shall be added as follows: 1- WALL THICKNESS SHALL BE IN ACCORDANCE WITH WALL THICKNESS CALCULATION REPORT. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | Noted. |  |  | Closed
5 | The material and Corrosion Allowance shall be specified for 4" Condensate Pipeline |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | According to calculations material should be C.S. + 6mm Corrosion allowance NACE. Relevant calculation will be presented in the next revision of Manifold corrosion study. This line exists and material selection is informative. |  |  | See Item 9
6 | تا زماني كه مدرك Piping corrosion study and Material Selection Report مربوط به منيفولد مورد تأييد نهايي كارفرما قرار نگيرد نمي توان در خصوص اين مدرك اظهار نظر قطعي نمود. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | مدرک مورد نیاز ارسال و توسط کارفرمای محترم تایید شده است.
7 | در دياگرام بايستي P&ID منيفولد نيز به عنوان مرجع در جدول ريفرنس ذكر گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | اعمال گردید.
8 | براي قسمت New Headerها نيز مشخصات متريال و CA درج گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | نقطه نظر کارفرمای محترم اعمال گردید.
9 | در دياگرام خط بصورت Existing 4" Condensate Pipeline معرفي گردد و توضيح پيمانكار در آيتم 5 فوق بصورت يك نوت در ديگرام اضافه گردد. |  | BK-SUR-ENG-PIP-01-06342 | 2022-12-04 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: