## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1731 |  |  | Transmital Date: 12/28/2022
Document Title: Line List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1731 |  |  | Transmital Date: 12/28/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0004_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تعدد نقطه نظرات، مجموعه نظرات در فایل PDF صفحه پیوست ارائه شده است |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | مدرک بر اساس آخرین تغییرات مدارک PID اصلاح گردید. لازم به ذکر است فایل PDF پیوست از جانب این پیمانکار دریافت نگردیده است
2 | مسئوليت تطابق اين مدرك با مدارك وابسته همچون PFD و P&ID با پيمانكار مي باشد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | مورد تایید است.
3 | ضروري است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: