## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-LI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1790 |  |  | Transmital Date: 1/14/2023
Document Title: Line List |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1790 |  |  | Transmital Date: 1/14/2023
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-LI-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ویرایش P&ID های مرجع، بر اساس آخرین ویرایش ارسال شده، اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | اصلاح گردید.
2 | کلاس شماره خط مقصد (to) ردیفهای خط 5 و23 به FN05 اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | اصلاح گردید.
3 | Sequence Number ردیفهای 3، 14، 15،18 و 19 اصلاح گردد. |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | موارد گفته شده در مدرک PID اعمال می شود.
4 | Radiography Testing ردیف 34 درج گردد (100%) |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | نقطه نظر کارفرمای محترم اعمال میگردد.
5 | برای خطوط لوله UG سیستم رنگ به صورت Solven Free Epoxy درج گردد. |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | نقطه نظر کارفرمای محترم اعمال میگردد.
6 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06850 | 2023-01-31 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: