## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2345 |  |  | Transmital Date: 9/5/2023
Document Title: Data Sheets For Pressure & Safety Relief Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2345 |  |  | Transmital Date: 9/5/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0009_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | یکسان سازی مدارک میبایست انجام گردد. به عنوان مثال Pset برای PSV-2101A/B/C برابر 9 Barg درج شده که میبایست اصلاح گردد. |  | 1402-2294-296011 | 1402/07/26 | مطابق آخرین P&ID اصلاح شد
2 | در خصوص متریال شیرآلات در این مرحله نظر خاصی مطرح نیست. تبادل نظر و نهایی سازی متریال مذکور در مرحله TBE با سازندگان صورت پذیرد. |  | 1402-2294-296011 | 1402/07/26 | در مرحله خرید نهایی خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: