## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1688 |  |  | Transmital Date: 12/11/2022
Document Title: PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1688 |  |  | Transmital Date: 12/11/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جدول تجهیزات بدون جزئیات فنی ذکر گردد. |  | 1401-2294-393787 | 1401/10/17 | با توجه به نظر کارفرمای محترم اصلاح گردید.
2 | برای جزئیات فنی به دیتاشیت و دیگر مدارک مهندسی مرتبط ارجاع داده شود. |  | 1401-2294-393787 | 1401/10/17 | با توجه به نظر کارفرمای محترم اصلاح گردید.
3 | جدول تجهیزات بجای قسمت جنرال مناسب است در قسمت SCOPE OF SUPPLY آورده شود. |  | 1401-2294-393787 | 1401/10/17 | با توجه به نظر کارفرمای محترم اصلاح گردید.
4 | در متن مدرک قبل از قسمت پیوست ها قید گردد: آخرین نسخه مدارک پیوست (نسخه نهایی) ملاک عمل می‌باشد. |  | 1401-2294-393787 | 1401/10/17 | با توجه به نظر کارفرمای محترم اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: