## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1688 |  |  | Transmital Date: 12/11/2022
Document Title: PMR For Pressure Safety Valves (PSV) - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1688 |  |  | Transmital Date: 12/11/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-IN-MR-0006_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG- INS-01-06526 | 2022-12-25 | ملاحظه گردید.
2 | مدرك Instrument & Control System Design Criteria در ليست مدارك مرجع درج گردد. |  | BK-SUR-ENG- INS-01-06526 | 2022-12-25 | در نسخه قبلی در مدارک ضمیمه یافت شد.
3 | با توجه به اينكه مدارك پيش نياز اين مدرك مانند ديتاشيت، داراي كامنت مي باشد و نهايي نيست (اطلاعات فرآيندي مورد قبول نمي باشد)، بعد از تاييد موارد فوق، اين مدرك مجددا جهت بررسي ارسال گردد. |  | BK-SUR-ENG- INS-01-06526 | 2022-12-25 | ملاحظه گردید.
4 | نقطه نظرات بخش QA/QC به پيوست ارائه مي گردد. |  | BK-SUR-ENG- INS-01-06526 | 2022-12-25 | بر روی فایل پیوست پاسخ داده شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: