## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0006_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2256 |  |  | Transmital Date: 23 Jul 2023
Document Title: PMR For Pressure Safety Valves (PSV) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2256 |  |  | Transmital Date: 23 Jul 2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بخش definition تکمیل گردد( عبارت sub-vendor) |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
2 | بخش abbreviation به مدرک اضافه و تمام کلمات مخفف استفاده شده در متن به مدرک اضافه شود. |  | 1402/2294/203643 | 1402/05/24 | مدرک مطابق فرمت کلی برای PMR ها تهیه شده است. کلمات کلیدی در Definition آورده شده است.
3 | در کل متن عبارت If any حذف گردد ( درجدولAttachment 2) |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
4 | در تمام متن عبارت Supplier به Vendor تغییر یابد. |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
5 | در بخش 5.1 عبارت QA به عبارت QA/QC تغییر یابد |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
6 | در attachment 1 مدرک BK-GNRAL-PEDCO-000-QC-PR-0045 با عنوان Packing , Marking, Transportation procedure به جدول اضافه گردد. |  | 1402/2294/203643 | 1402/05/24 | در ایتم شماره ۳۷ جدول آورده شده است
7 | در attachment 1 به ورژن مدارک دقت شود( بعنوان مثال ردیف های ۳۳و۳۴و۳۶) در مجموع متذکر میشود آخرین نسخه مدارک پیوست ( نسخه نهایی) ملاک عمل میباشد. |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
8 | در Attachment 2 ردیف ۳۲ باید به تایید کافرما برسد و در ستون Purpose حرف I به A تغییر یابد |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
8 | در Attachment 2 ربرای ردیف های ۳۳ و۳۷ در ستون Q/type عبارت 4N درج گردد |  | 1402/2294/203643 | 1402/05/24 | مطابق خواست کارفرمای محترم اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 23 Jul 2023 |  |  |  |  | Date: