## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PR-PI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1731 |  |  | Transmital Date:12/28/2022
Document Title: P&ID - Gas Pipeline (to Siahmakan G.I. Station) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1731 |  |  | Transmital Date:12/28/2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-PR-PI-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شیرهای PSV یه صورت فلنجی نمایش داده شود. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
2 | کلیه شیرهای با اندازه 2 اینچ و بزرگتر از آن به صورت فلنجی نمایش داده شود. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
3 | شماره و سایز نازلهای تجهیز مشخص گردد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
4 | میزان شیب خطوط مشخص گردد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
5 | برای خط بالا دست خط-FLG-113-0003-AN07-3 (صفحه 1) می بایست شماره خط با کلاس FN06 در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
6 | با توجه به سایز 2 اینچ خروجی PSV-3201، لزوم در نظر گرفتن Expander در خروجی آن مشخص نمی باشد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
7 | لازم است نقطه نظرات ذينفع اصلي اعمال گردد. |  | BK-SUR-ENG-PCS-01-06633 | 2023-01-08 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021