## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1920 |  |  | Transmital Date: 3/1/2023
Document Title: Duty Specification for Chemical Injection Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1920 |  |  | Transmital Date: 3/1/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-SP-0004_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهایی سازی مدارک منوط به ارائه پیشنهاد تولید کننده مواد شیمیایی در خصوص میزان مصرف و جزییات مربوطه از قبیل پمپ تزریق و مخزن در مدرک Chemical Consumption می باشد که این مهم تاکنون مخقق نشده است. |  | 1401/2294/197103 | 1401/05/18 | بر اساس صورتجلسه با آن کارفرمای محترم مقرر گردید میزان تزریق مواد شیمیایی برابر با 0.5 Pint به ازای هر MMSCF با رقیق سازی 30 به 70 و ضزفیت مخزن نیز 1M3 در نظر گرفته شود که این مهم در مدرک Chemical Consumption به شماره مدرک "BK-GCS-PEDCO-120-PR-LI-0005" و مدرک فوق اعمال گردید و مدرک به صورت AFC به حضور ایفاد می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021

## Sheet3
33.99