## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-SA-LI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1399 |  |  | Transmital Date: 11/09/2022
Document Title: Hazard Source List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SA-TR-1399 |  |  | Transmital Date: 11/09/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-SA-LI-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توضیحات ارائه شده در خصوص بند 2 نامه این امور مورد تائید نمی باشد و لازم است در جدول صفحه 5 ، ترکیب درصد سیال ورودی سایت ذکر گردد. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
2 | توضیحات ارائه شده در خصوص بند 4 نامه این امور مورد تائید نمی باشد و لازم است در خصوص تجهیزات درون sump، لازم است شکل شماره 101 لحاظ شود. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
3 | توضیحات ارائه شده در خصوص بند 7 نامه این امور مورد تائید نمی باشد و لازم است در خصوص تجهیز ردیف 36 شکل شماره 96 ذکر گردد. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
4 | کلاس دمایی مربوط به اتاق باطری بر اساس استاندارد T3 لحاظ گردد. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
5 | لازم است گروه گازی تجهیزات مورد بازنگری قرار گیرد. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
6 | در خصوص تجهیزات ردیف 27و28 و 30 شکل استاندارد مورد بازنگری قرار گیرد. |  | 1401-2294-316902 | 1401/08/29 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: