## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-SA-PY-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0715 |  |  | Transmital Date: 12/03/2022
Document Title: Hazardous Calssification Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-SA-TR-0715 |  |  | Transmital Date: 12/03/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-SA-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | باتوجه به وضوح پایین نقشه امکان بررسی نوع و شعاع زون ها وجود ندارد. لذا لازم است نقشه با وضوح بهتر جهت بررسی به این امور ارسال گردد. |  | 1401-2294-16831 | 1401/01/21 | خواهشمند است از کلید CTRL+5 برای مشاهده بهتر نقشه استفاده نمایید.
2 | کلاس دمایی اتاق باطری در قسمت T3، noteذکر گردد. |  | 1401-2294-16831 | 1401/01/21 | اعمال می گردد.
3 | در قسمت note طبقه بندی منطقه خطر مربوط به اتصالات و ولو ها ذکر گردد. |  | 1401-2294-16831 | 1401/01/21 | اعمال می گردد.
4 | نمای جانبی طبقه بندی منطقه خطر تجهیزات بر اساس استاندارد API-RP-505 به مدرک اضافه گردد. |  | 1401-2294-16831 | 1401/01/21 | اعمال می گردد.
5 | نقطه نظرات این امور در خصوص مدرک Hazard source list در این مدرک اعمال گردد. پیشنهاد می شود پس از نهایی شدن مدرک Hazard source list مدرک فوق جهت بررسی به این امور ارسال گردد. |  | 1401-2294-16831 | 1401/01/21 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: