## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2250 |  |  | Transmital Date:7/18/2023
Document Title: Geotechnical Investigation Report - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2250 |  |  | Transmital Date:7/18/2023
[5 empty] | CRS No:NISOC-CRS-BK-W028-PEDCO-110-GT-RT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-246617 | 1402/06/22 | انجام شد.
2 |  |  | 1402-2294-246617 | 1402/06/22 | جمله زیر در بخش 8-1 صفحه 66 گزارش اضافه شد: • در محدوده گمانه¬های حفاری شده به پدیده کارست برخورد نشده است.
3 |  |  | 1402-2294-246617 | 1402/06/22 | عبارت زیر در بخش 8-2 صفحه 65 اضافه شد: • میزان نفوذپذیری در لایه‌های خاک متراکم و سنگ مشاهده شده در گمانه‌های ماشینی بسته‌ی W-007S بسیار ناچیز و بر اساس مراجعی مانند Wyllie and Mah (2004) در حدود 10-6 الی 10-7 سانتیمتر بر ثانیه می‌باشد
4 |  |  | 1402-2294-246617 | 1402/06/22 | در بخش 8-2 گزارش صفحه 66 توضیح زیر اضافه شده است: باتوجه به تعداد روزهای ناچیز یخبندان در ایستگاه های موجود در اطراف پروژه، عمق یخبندان ناچیز برآورد می شود.
5 |  |  | 1402-2294-246617 | 1402/06/22 | گزارش منابع قرضه در پیوست شماره 6 گزارش اضافه شد. توصیه های عملیات خاکریزی و اصلاح بستر در انتهای بخش 8-2 صفحات 71 و 72 موجود می باشد. توضیحات تفصیلی در نشریات 101 و 268 سازمان مدیریت و برنامه ریزی کشور ارائه شده است.
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: