## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2239 |  |  | Transmital Date:1402/04/01
Document Title: Geotechnical Investigation Report - W046S |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2239 |  |  | Transmital Date:1402/04/01
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-GT-RT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-285563 | 1402/07/22 | انجام شد.
2 |  |  | 1402-2294-285563 | 1402/07/22 | گزارش منابع قرضه در پیوست شماره 6 گزارش اضافه شد. توصیه های عملیات خاکریزی، اساس و زیراساس و اصلاح بستر در انتهای بخش 8-2 صفحات 60، 61 و 62 موجود می باشد. توضیحات تفصیلی در نشریات 101 و 268 سازمان مدیریت و برنامه ریزی کشور ارائه شده است.
3 |  |  | 1402-2294-285563 | 1402/07/22 | جمله زیر به بخش 5-4 (صفحه 39) گزارش اضافه شد: این تمهیدات می¬تواند حفاظت اطراف پی¬ها برای جلوگیری از نفوذ آب و برداشتن لایه خاک متورم شونده در صورت کم بودن ضخامت آن (بر اساس لاگ گمانه¬ها) باشد.
4 |  |  | 1402-2294-285563 | 1402/07/22 | حذف شد.
5 |  |  | 1402-2294-285563 | 1402/07/22 | جمله زیر به بخش 4-2-3 (صفحه 32) گزارش اضافه شد: بر اساس نتیجه به دست آمده از آزمایش¬های CBR، سطح کیفی مصالح خاکی نسبتاً خوب (fair) ارزیابی شده و برای استفاده در زیر اساس می¬تواند مناسب باشد (Bowles, 1995).
6 |  |  | 1402-2294-285563 | 1402/07/22 | در شرح خدمات اولیه حداکثر عمق حفاری گمانه ها 3 متر می باشد و در خصوص افزایش عمق گمانه گمانه و یا افزایش تعداد گمانه ها در محلهایی که خاک دستی تا انتهای گمانه وجود دارد، در شرح خدمات مطلبی عنوان نشده است. لذا با عنایت به جمع آوری کارگاه، انجام خدمات تکمیلی ذکر شده در ردیف 9 مستلزم صرف هزینه مجدد تجهیز کارگاه و حفاری از سوی کارفرمای محترم می باشد. لذا پیشنهاد می گردد عمق خاک دستی حین ساخت تعیین گردد.
7 |  |  | 1402-2294-285563 | 1402/07/22 | چنین کامنتی در کامنت شیت کارفرما یافت نشد. لیکن مطالعات ژئوتکنیک در محلهای مشخص شده توسط شرکت هیرگان انرژی انجام شده است.
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: