## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK05-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2240 |  |  | Transmital Date:6/22/2023
Document Title: Geotechnical Investigation Report - BK05 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2240 |  |  | Transmital Date:6/22/2023
[5 empty] | CRS No:NISOC-CRS-BK-BK05-PEDCO-110-GT-RT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-264584 | 1402/07/08 | جمله زیر به صفحه 31 و 32 گزارش اضافه شد: بر اساس نتیجه به دست آمده از آزمایش CBR، سطح کیفی مصالح خاکی نسبتاً خوب (fair) ارزیابی شده و برای استفاده در زیر اساس می¬تواند مناسب باشد.
2 |  |  | 1402-2294-264584 | 1402/07/08 | انجام شد.
3 |  |  | 1402-2294-264584 | 1402/07/08 | گزارش منابع قرضه در پیوست شماره 6 ارائه شده است.
4 |  |  | 1402-2294-264584 | 1402/07/08 | توضیحات مربوطه در صفحه 38 گزارش موجود می باشد.
5 |  |  | 1402-2294-264584 | 1402/07/08 | توضیحات مربوط به عمق یخبندان در بند چهارم بخش 8-2 گزارش ژئوتکنیک وجود دارد.
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: