## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-IN-TB-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1603 |  |  | Transmital Date: 26 Nov 2022
Document Title: TBE/TBA For Instrument Bulk Items |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1603 |  |  | Transmital Date: 26 Nov 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W008N-PEDCO-110-IN-TB-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06317 | 2022-12-03 | مطابق نامه شماره ص ت ب/۱۴۸۱۴ مورخ ۱۴۰۲.۰۸.۲۳ مدرک از طرف شرکت پترو ایران No Comment در نظر گرفته شده است.
2 | مطابق شرايط پيمان تمامي وندورها بايستي در ليست AVL باشند. در صورت تاييد كارفرما موارد قابل بررسي مي باشد. ضمنا مي بايست مستندات مربوط به كيفيت تجهيزات جهت بررسي بيشتر ارائه گردد. |  | BK-SUR-ENG-INS-01-06317 | 2022-12-03
3 | جدول Technical Exception/Deviation List بايستي براي تمامي وندورها در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06317 | 2022-12-03
4 | با توجه به نهايي نبودن مدارك مسئوليت تعداد و نوع ادوات ارائه شده بر عهده پيمانكار فرعي (هيرگان انرژي) مي باشد. |  | BK-SUR-ENG-INS-01-06317 | 2022-12-03
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 Dec 2022 |  |  |  |  | Date: