## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-IN-TB-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1553 |  |  | Transmital Date: 25 Oct 2022
Document Title: TBE/TBA For Instrument Bulk Items - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1553 |  |  | Transmital Date: 25 Oct 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W028-PEDCO-110-IN-TB-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ليست Deviation تمام وندورها ارائه شود. |  | BK-SUR-ENG-INS-01-06134 | 2022-11-08 | مطابق نامه شماره ص ت ب/۱۴۸۱۴ مورخ ۱۴۰۲.۰۸.۲۳ مدرک از طرف شرکت پترو ایران No Comment در نظر گرفته شده است.
2 | لازم به ذكر است كه تمامي وندورها بايد مطابقت با AVL باشد. |  | BK-SUR-ENG-INS-01-06134 | 2022-11-08
3 | براي Tube ها بايد استاندارد NACE در نظر گرفته شود |  | BK-SUR-ENG-INS-01-06134 | 2022-11-08
4 | گارانتي براي تمامي وندورها مطابق با قرارداد باشد. |  | BK-SUR-ENG-INS-01-06134 | 2022-11-08
5 | لازم به ذكر است كه در صورت تاييد كارفرما بر روي مدرك فوق، اين مدرك از نظر اين امور قابل بررسي و تاييد مي باشد. |  | BK-SUR-ENG-INS-01-06134 | 2022-11-08
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 8 Nov 2022 |  |  |  |  | Date: