## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-MR-0018_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2009 |  |  | Transmital Date: 9 Apr 2023
Document Title: PMR For Instrument Cable Tray/Ladder - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2009 |  |  | Transmital Date: 9 Apr 2023
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-MR-0018_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تاییداست ولیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخ تایید شده (AFC) است. معالذالک جهت پرهیز ار مکاتبات مضاعف وتسریع در تایید مدارک فوق ، نهایی سازی مدارک پیش نیاز ( که در پیوست ۱ مدرک اشاره شده است) دردستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1402/2294/74530 | 1402/02/31 | مدرک مطابق آخرین نسخه از مدارک پیش نیاز تهیه گردید.
2 | مزید تاکیداعلام میگردد از آنجا که مسئولیت طراحی تفضیلی پروژه جزو تعهدات پیمانکار پروژه بوده و همچنین با استنادبه وضعیت مدارک ارسالی (IFI) ، مسئولیت کامل عدم تطابق مندرج در این مدارک (مشخصات فنی و یا تعداد) درمرحله سفارش گذاری و خریدبه عهده ان پیمانکر میباشد. |  | 1402/2294/74530 | 1402/02/31 | .ملاحظه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 Apr 2023 |  |  |  |  | Date: