## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0057 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2391 |  |  | Transmital Date:9/27/2023
Document Title: Foundation Drawing For Chemical Injection and Storage Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0026-ST-T-2391 |  |  | Transmital Date:9/27/2023
[5 empty] | CRS No:PEDCO-CRS- BK-GCS-PEDCO-120-ST-DW-0057_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-310722 | 1402/08/06 | به استحضار می رساند اصولا مدارک به همراه فایل و دفترچه محاسبات برای آن کارفرمای محترم ارسال می گردد.
2 |  |  | 1402-2294-310722 | 1402/08/06 | این نقشه ها در مدارک سیویل ارائه گردیده است و در قسمت رفرنس ها اضافه گردید.
3 |  |  | 1402-2294-310722 | 1402/08/06 | تمامی گیرت ها با آخرین مدرک معماری مطابقت داده شد.
4 |  |  | 1402-2294-310722 | 1402/08/06 | در دیتیل 12 شیت 3 تمامی استیفنرها نمایش داده شده است.
5 |  |  | 1402-2294-310722 | 1402/08/06 | کنترل گردید و تغیررات اعمال گردید.
6 |  |  | 1402-2294-310722 | 1402/08/06 | در قسمت رفرنس ها تمامی مدارک قید شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: