## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0030_D06 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2251 |  |  | Transmital Date: 18/JULY/2023
Document Title: Mechanical Data Sheets For Fire Water Main Pumps - Diesel Engine Driven |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0204-ME-TR-2251 |  |  | Transmital Date: 18/JULY/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0030_D06 |  |  | CRS Status: | C1
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
| در این برهه نظر خاصی مطرح نمی باشد.از این رو پیشبرد گام بعدی مهندسی بلامانع است. شایان ذکر است با توجه به مفاد 13 شرایط عمومی پیمان, مسئولیت هر نوع نقص و کمبود در نقشه ها و مدارک فنی در محدوده پروژه و در هر مقطع از پروژه اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-MEC-02-08105 | 2023-07-19
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: | Signature
Date: 7/19/2023