## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0066 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2294 |  |  | Transmital Date:8/9/2023
Document Title: Structural Drawing For Fire Water Pump Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-T-2294 |  |  | Transmital Date:8/9/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-ST-DW-0066_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-244607 | 1402/06/21 | فایل محاسبات سازه و دیتا شیت تجهیزات به پیوست ارائه می گردد
2 |  |  | 1402-2294-244607 | 1402/06/21 | مطابق با متن قرارداد در نظر گرفته شده است
3 |  |  | 1402-2294-244607 | 1402/06/21 | دیتا شیت جهت طراحی فونداسیون تجهیزات در مدرک مربوطه ارائه می گردد
4 |  |  | 1402-2294-244607 | 1402/06/21 | محاسبات بر اساس پارامتر های استخراج شده از مدرک ژئوتکنیک مربوط به GCS انجام شده است
5 |  |  | 1402-2294-244607 | 1402/06/21
6 |  |  | 1402-2294-244607 | 1402/06/21 | طول سرکش یا کنسول ساییبان در مدارک معماری و سازه برابر 100 سانتیمتر می باشد
7 |  |  | 1402-2294-244607 | 1402/06/21 | اعمال گردید.
8 |  |  | 1402-2294-244607 | 1402/06/21 | اعمال گردید.
9 |  |  | 1402-2294-244607 | 1402/06/21 | در ردیف شماره 5 نقشه فونداسیون درج شده است
10 |  |  | 1402-2294-244607 | 1402/06/21 | جهت تراز زیر بیس پلیت ضخامت 25 میلیمتر کفایت می کند
11 |  |  | 1402-2294-244607 | 1402/06/21 | نمایش داده شده است
12 |  |  | 1402-2294-244607 | 1402/06/21 | به نوت نقشه ها اضافه گردید
13 |  |  | 1402-2294-244607 | 1402/06/21 | به مدرک STANDARD DRAWING FOR FIREPROOFING اشاره گردید
14 |  |  | 1402-2294-244607 | 1402/06/21 | سازه های ایستگاه کمپرسور به صورت LOCAL در نظر گرفته شده است
15 |  |  | 1402-2294-244607 | 1402/06/21 | اعمال گردید.
16 |  |  | 1402-2294-244607 | 1402/06/21 | اعمال گردید.
17 |  |  | 1402-2294-244607 | 1402/06/21 | #
18 |  |  | 1402-2294-244607 | 1402/06/21 | ترازهای نمایش شده بدلیل اشاره به اعضا ، در تراز های متفوت می باشد.
19 |  |  | 1402-2294-244607 | 1402/06/21 | اعمال گردید.
20 |  |  | 1402-2294-244607 | 1402/06/21 | #
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: