## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-BD-0001_D06 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2260 |  |  | Transmital Date: 23 Jul 2023
Document Title: Control/ESD/F&G System Block Diagram Configuration |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 2260 |  |  | Transmital Date:23 Jul 2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است F&G OPERATOR WORKS STATION خارج از اتاق مهندسی در نظر گرفته شود. |  | 1402/2294/232373 | 1402/06/13 | با توجه به توافقات صورت گرفته OPERATOR WORKSTATION و ENGINEERING WORKSTATION مربوط به سیستم F&G ادغام گردیده است و تبدیل به ES/OS WORKSTATION گردیده است بنابر این جانمایی مربوطه در اتاق مهندسی لحاظ گردیده است.
2
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Jul 2023 |  |  |  |  | Date: