## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-BD-0001_D06 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2260 |  |  | Transmital Date: 23 Jul 2023
Document Title: Control/ESD/F&G System Block Diagram Configuration |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2260 |  |  | Transmital Date:23 Jul 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-BD-0001_D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Connection from this package to F&G and from ESD to be shown. |  | BK-SUR-ENG-INS-02-08202 | 2023-08-01 | ارتباطی با سیستم ESD وجود ندارد.
2 | Type of package to be added. |  | BK-SUR-ENG-INS-02-08202 | 2023-08-01 | تایپ پکیج از نوع A میباشد و اضافه گردید.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Jul 2023 |  |  |  |  | Date: