## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0017_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1703 |  |  | Transmital Date: 17 Dec 2022
Document Title: Data Sheets For ESD Console/F&G Matrix Panel |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1703 |  |  | Transmital Date: 17 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DT-0017_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | شماتيك هاي ارائه شده با جدول ارائه شده همخواني ندارد |  | BK-SUR-ENG-INS-01-06593 | 2023-01-02 | اصلاح گردید.
2 | تناقض بين موارد با مدرك hirarichy وجود دراد، موارد PB و Lamp نهايي و در مدرك اضافه شود. |  | BK-SUR-ENG-INS-01-06593 | 2023-01-02 | بر اساس مدرک hirarichy برای تمامی سطوح 0,1,1A,2,2A پوش باتن و چراغ سیگنال مربوطه در نظر گرفته شده است.
3 | با توجه به نهايي نبودن مدارك پيش نياز مانند C&E، موارد در صورت تغيير در اين مدرك نيز ارائه گردد. |  | BK-SUR-ENG-INS-01-06593 | 2023-01-02 | چنانچه در سطوح ESD تغییری حاصل گردید مدرک مربوطه به روز خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Jan 2023 |  |  |  |  | Date: