## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2239 |  |  | Transmital Date:6/22/2023
Document Title: Geotechnical Investigation Report - W008N |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2239 |  |  | Transmital Date:6/22/2023
[5 empty] | CRS No:NISOC-CRS-BK-W008N-PEDCO-110-GT-RT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-285563 | 1402/07/22 | انجام شد.
2 |  |  | 1402-2294-285563 | 1402/07/22 | عبارت زیر به بند دوم بخش 8-2 صفحه 48 اضافه شد: • میزان نفوذپذیری در لایه‌های خاک متراکم و سنگ مشاهده شده در گمانه‌های ماشینی بسته‌ی W-007S بسیار ناچیز و بر اساس مراجعی مانند Wyllie and Mah (2004) در حدود 10-6 الی 10-7 سانتیمتر بر ثانیه می‌باشد
3 |  |  | 1402-2294-285563 | 1402/07/22 | ردیف 4: گزارش منابع قرضه در پیوست شماره 6 اضافه شد. ردیف 5 و 9: توصیه های عملیات خاکریزی و اصلاح بستر در انتهای بخش 8-2 صفحات 49 تا 51 اضافه شد. توضیحات تفصیلی در نشریات 101 و 268 سازمان مدیریت و برنامه ریزی کشور ارائه شده است.
4 |  |  | 1402-2294-285563 | 1402/07/22 | در موقعیت هایی که تعداد گمانه کافی و با فاصله مناسب برای رسم پروفیل وجود داشته، رسم پروفیلها قابل انجام می باشد، لذا در گزارشهای مربوطه انجام شده است. در سایر محلها به دلیل اختلاف تراز زیاد و فاصله نسبتاً طولانی، رسم پروفیل خاک با خطای زیاد و عدم پیوستگی همراه خواهد بود.
5 |  |  | 1402-2294-285563 | 1402/07/22 | در انتهای بخش 8-2 صفحات 49 تا 51 گزارش ارائه شده است.
6 |  |  | 1402-2294-285563 | 1402/07/22 | چنین کامنتی در کامنت شیت کارفرما یافت نشد لیکن مطالعات ژئوتکنیک در محلهای مشخص شده توسط شرکت هیرگان انرژی انجام شده است.
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: