## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-IN-MR-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1351 |  |  | Transmital Date: 04 Sep 2022
Document Title: PMR For Instrument Bulk Items - W046S |  |  |  |  | PEDCO Tr. No.: |  |  | Transmital Date: 04 Sep 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-IN-MR-0003_D01 |  |  | CRS Status: | C2
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
INSTRUMENT DEPARTMENT COMMENTS
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده وي است. |  |  | 2022-09-18 | مطابق نامه شماره ص ت ب/۱۴۸۱۴ مورخ ۱۴۰۲.۰۸.۲۳ مدرک از طرف شرکت پترو ایران No Comment در نظر گرفته شده است.
2 | Min Requirement ها براي ITP در مدرك آورده شود. (Monitoring/Review/witness) |  |  | 2022-09-18
3 | Quality Control Plan (QCP) بر اساس مدارك پروژه مشخص شود. |  |  | 2022-09-18
4 | براي Trace راحت تر مدرك در يكي از ضمايم، مسئوليت هاي مربوط به Vendor و Purchaser مشخص شود. |  |  | 2022-09-18
5 | با توجه به اينكه spec، Data sheet و Index نهايي نيست، اين مدرك نهايي نبوده و در صورت هر گونه تغيير در مدارك پيش نياز در اين مدرك نيز اصلاح شود. |  |  | 2022-09-18
QC DEPARTMENT COMMENTS
6 | در جدول بند 11.2: - ستونهاي " After Ordering" و "At The Final Inspection" به "For Review" و "Final Issue" تغيير يافته و اين مورد در تمامي MR ها رعايت شده و از فرمت تاييد شده استفاده گردد. -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-INS-00-02831 | 2022-09-18 | مطابق نامه شماره ص ت ب/۱۴۸۱۴ مورخ ۱۴۰۲.۰۸.۲۳ مدرک از طرف شرکت پترو ایران No Comment در نظر گرفته شده است.
5 | در بند 6، مدرك E&C-QC-IN-SP-1 حذف شده و دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  |  | 2022-09-18
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 Sep 2022 |  |  |  |  | Date: