## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-SP-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2445 |  |  | Transmital Date: 10/21/2023
Document Title: Piping Material Specification |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2445 |  |  | Transmital Date: 10/21/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-SP-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در كلاسهاي CN05 و CN07 و FN05 و FN07 و CS00 و FS00 درجه حرارت طراحي بر اساس دماي خروجي كمپرسور و كولر هوايي اصلاح گردند. در صفحه 14 بخش 7.2 جدول 1 و جداول بخش 8 اصلاحات لازم اعمال گردد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | - اعمال گردید. |  |  | Closed
2 | در جداول بخش 8 سرويس هاي ذكر شده در كلاسهاي مختلف با جدول 1 در بخش 7.2 مطابق باشد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | - اعمال گردید. |  |  | Closed
3 | در كلاس FN07 كد طراحي به ASME B31.3 اصلاح گردد. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | نقطه نظر کارفرمای محترم اعمال گردید. |  |  | Closed
4 | با توجه به كامنت ارائه شده در مدرك Wall Thickness Calculation Report در صورت هرگونه تغيير ضخامت لوله در مدرك PMS لحاظ گردد.. |  | BK-SUR-ENG-PIP-01-05962 | 2022-10-24 | نقطه نظر کارفرمای محترم اعمال گردید.
5 | از آنجا كه مطابق مدرك مطالعات خوردگي تمامي Streamهاي خطوط فرآيندي سرويس ترش بوده و نيازمندي هاي NACE MR-0175 بايستي در نظر گرفته شود، خطوط Closed Drain‌متصل به اين خطوط نيز كه Wet H2S environment مي باشند بايستي مطابق با نيازمندي هاي NACE در نظر گرفته شوند. لذا تمامي متريال كلاس هاي AS00 و CS00 و FS00 كه شامل سرويس هاي Closed Drain‌و Process Gas نيز مي باشند بايستي مطابق NACE MR-0175 باشند. بدين منظور يا بايستي در كلاس هاي مذكور براي كل سرويس ها NACE ذكر گردد يا اينكه كلاس هاي جديدي با نيازمندي NACE براي خطوط استنلس استيل حاوي سرويس هاي Closed Drain و Process Gas تعريف گردد. |  | BK-SUR-ENG-PIP-02-08648 | 2023-10-23 | این موضوع به صورت Note لحاظ گردیده و در دیتاشیت ها و همچنینMTO اعمال می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:10/23/2023 |  |  |  |  | Date:10/23/2023