## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-IN-SP-0003_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1255 |  |  | Transmital Date: 6 Aug 2022
Document Title: Specification For ESD System |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1255 |  |  | Transmital Date: 6 Aug 2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-IN-SP-0003_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص مورد 1 REPLY SHEET متن اصلاح گردد برای بسته خطوط لوله تجهیزات ESD پایه رله ای SIL3 جدید در پنل های موجود نصب می شوند. |  | 1401-2294-240310 | 1401/07/06 | مطابق خواست کارفرمای محترم اصلاح شد.
2 | در خصوص مورد 5 با توجه به نهایی نشدن مدرک زیربرای برخی از بسته ها تعداد و ارایش ایستگاه کاری /مهندسی(E/OWS) متناسب با این مدرک برای هر بسته مورد بازنگری قرار گیرد.control/esd/dcs/f&g/ sysytem block diagram configuration |  | 1401-2294-240310 | 1401/07/06 | تغیییرات لازم متناسب با این مدرک صورت پذیرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 20 Aug 2022 |  |  |  |  | Date: