## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2290 |  |  | Transmital Date:2023/08/07
Architectural Drawing For CCTV Rack Room- Binak PU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-2290 |  |  | Transmital Date: 2023/08/07
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0010 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بندهای 1،2،11،21 نامه قبلی به شماره 136306 مورخ 1402/04/10 کماکان به قوت خویش باقی است، لذا در ویرایش آتی مدرک ارائه گردد. در این خصوص کد فینیش گریدینگ در فایل پاسخنامه پیمانکار11.20 و در نقشه 36.30 درج شده که مغایرت دارد.بازنگری و اصلاح گردد. |  | 1402-2294-223974 | 1402/06/06 | بند1: جانمایی ساختمان اصلاح گردید. بند2: کد F.G.L اصلاح شد. بند11: دیچ مربوطه پس از نهایی سازی اصلاح میگردد. بند21: تجهیزات سرمایش و گرمایش توسط بخش HVAC بررسی و در نقشه ها اعمال گردید. - تجهیزات سیستم اعلان حریق به صورت رو کار انجام خواهد شد و نیازی به سوراخ کاری نمی باشد.
2 | کد مدرک پلات پلن مربوطه در فهرست مراجع درج گردد. |  | 1402-2294-223974 | 1402/06/06 | محل موردنظر مربوطه در EXISTING AREA می باشد.
3 | نوع پنجره ها از فلزی بهUPVC اصلاح گردد. |  | 1402-2294-223974 | 1402/06/06 | پنجره ها به UPVC اصلاح گردید.
4 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
5
6 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
7 | Commented By: | Signature |  |  |  | Clarified By: | Signature
8
9 | Date: |  |  |  |  | Date:
10
11
12
13
14
15
16
17
18
19
20
21
22
Legend
Signature
21
Legend
Signature