## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-MR-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1357 |  |  | Transmital Date: 05-Sep-2022
Document Title: PMR For LV Switchgear, MCC |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1357 |  |  | Transmital Date: 05-Sep-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-EL-MR-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه برخی از مدارک پیش نیاز این مدرکاز جمله لیست بارها و دیاگرام تک خطی و لاجیک دیاگرام تاکنون تأیید نهایی نشده است، مقتضی است پس از تأیید این مدارک توسط کارفرما شماره آخرین ویرایش در مدرک درج گردد. |  | 1401-2294-216049 | 1401-06-17 | مدارک مرتبط همگی تا آخرین ویرایش مورد بازبینی قرار گرفته است. از اینرو می توان نسبت به خرید تابلو و بانک خازنی اقدام نمود. لازم به ذکر است این مدرک همواره در حال به روزرسانی خواهد بود و در اختیار سازنده تابلوها قرار خواهد گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 13-Sep-22 |  |  |  |  | Date: