## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-SL-0002_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1915 |  |  | Transmital Date: 27-Feb-2022
Document Title: LV Switchgear/MCC Single Line Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0112-EL-TR-1915 |  |  | Transmital Date: 27-Feb-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-EL-SL-0002_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقتضی است بر اساس آخرین کامنتهای این امور مندرج در نامه شماره 496694 مورخ 1401-12-27 پس از نهایی شدن مدرک لیست بار الکتریکال، این مدرک مورد بازنگری قرار گیرد. |  | 1401-2294-498404 | 1401-12-28 | مدرک لیست بار مطابق با آخرین توانهای مصرفی بخش مکانیک در حال به روزرسانی میباشد که نتیجه آن در مدرک لیست کابل با شماره ترنسمیتال 2487 منعکس شده و برای آن کارفرمای محترم ارسال شده است. در حال حاضر لیست بار و لیست کابل تقریبا نهایی می باشد و جهت خرید تابلوهای LV می توان به آن استناد نمود. همچنین تمام تابلوهای LV مورد نیاز شرکت هوایار به مدرک اضافه شده است. با این حال مدرک لیست بار به روزرسانی خواهد شد و ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 11-Mar-23 |  |  |  |  | Date: