## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0010_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1073 |  |  | Transmital Date: 6/14/2022
Document Title: F&G Cause and Effect Diagram For Building |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR- 1073 |  |  | Transmital Date: 6/14/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DG-0010_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص مدرک فوق منوط به نهایی شدن نقشه جا نمایی سیستم اعلان حریق و سایر مدارک مرتبط می باشد. |  | 1401-2294-180898 | 1401/05/25 | مدرک مورد اشاره با اخرین رویژن نقشه جا نمایی سیستم اعلان حریق مورد بازبینی قرار گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 25 Oct 2022 |  |  |  |  | Date: