## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2264 |  |  | Transmital Date: 24 Jul 2023
Document Title: Instrument Location Layout |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-2264 |  |  | Transmital Date: 24 Jul 2023
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک مرجع (REFRENCE ) کامل و دقیق ذکر شود |  | 1402-2294-201666 | 1402/05/23 | مطابق خواست کارفرمای محترم اعمال گردید
2 | در LAYOUT مربوطه برخی از تجهیزات در نظر گرفته نشده اند بعنوان مثال برخی از FT , FE ها |  | 1402-2294-201666 | 1402/05/23 | مطابق خواست کارفرمای محترم اعمال گردیدو مطابق اخرین مدارک بروز رسانی شد.
3 | محل نصب برخی از تجهیزات درست در نظر گرفته نشده است بخصوص تجهیزاتی که روی خط نصب نمی شوند و محل نصب آنها روی ساپورت است |  | 1402-2294-201666 | 1402/05/23 | محل انشعاب از خط به عنوان نقطه اندازه گیری شده در نقشه نشان داده شده است. محل نصب ساپورت ها در مدل ۳ بعدی نمایش داده شده است و در سایت نهایی سازی خواهد شد.
4 | در مورد ESDV ها نمایش سلونویید ولو آنها در نظر گرفته نشده است |  | 1402-2294-201666 | 1402/05/23 | به دلیل فشردگی نقشه تنها شیر اصلی نشان داده شده است. خواهشمند است Tag هر تجهیز به همراه کلیه اکسسوری ها مطابق دیتا شیت فرض شود(همه اکسسوری ها نیز برروی تجهیز نصب خواهد شد)
5
6
7
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: