## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2264 |  |  | Transmital Date: 24 Jul 2023
Document Title: Instrument Location Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2264 |  |  | Transmital Date: 24 Jul 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  |  | 2023-08-07 | ملاحظه گردید
2 | با توجه به اينكه مدل 90% كه تجهيزات ابزاردقيق در آن نهايي مي گردد ارائه نشده است، اين مدرك تا زمان ارائه شدن آن مدرك قابليت تاييد را ندارد. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | مطابق آخرین مدل به روز رسانی شد و شماره گزارش مربوطه به عنوان refrence اضافه شد
3 | پاسخ كامنت شماره 5 در مدرك پيشين قابل قبول نبوده و نواحي zone بندي شده در صفحه 3 در اين مدرك جهت خوانايي مدرك مشخص شود. همچنين نام و شماره equipment ها، در هر صفحه مشخص گردد. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | صفحه 4(PLOT ) اضافه شد
4 | مدل 90% نيز بعنوان مدرك مرجع اضافه گردد. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | اعمال شد
5 | مدرك plot plan نيز بعنوان مدارك مرجع اضافه گردد. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | اعمال شد
6 | محل قرار گيري JB ها مشخص شود. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | در مدرک CABLE ROUTE نشان داده شده است و این مدرک بعنوان REFRENCE اضافه شده است
7 | فضاي دسترسي در مدل 90 درصد بررسي خواهد شد و بر اساس آن مدرك به روز رساني گردد. |  | BK-SUR-ENG-INS-02-08236 | 2023-08-07 | مطابق آخرین مدل به روز رسانی شد و شماره گزارش مربوطه به عنوان refrence اضافه شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 7 Aug 2023 |  |  |  |  | Date: