## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1738 |  |  | Transmital Date: 28 Dec 2022
Document Title: PMR For ESD System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR- 1738 |  |  | Transmital Date: 28 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06659 | 2023-01-16 | ملاحظه شد.
2 | در بند 5.3، عبارت QA Organization به QA/QC Organization تغییر یابد. |  | BK-SUR-ENG-INS-01-06659 | 2023-01-16 | مطابق درخواست کارفرمای محترم انجام شد.
3 | در بند 7 عبارت زیر اضافه شود: "سازنده میبایست مدارک ITP، QCP و MPS را قبل از برگزاری جلسه PIM جهت بررسی ارائه دهد." |  | BK-SUR-ENG-INS-01-06659 | 2023-01-16 | این مدارک در قسمت 11.2 VENDOR DOCUMENTS MIN. REQUIREMENT در مرحله Bid از سازنده خواسته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Jan 2023 |  |  |  |  | Date: