## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0085 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2469 |  |  | Transmital Date:11/6/2023
Document Title: Structural Drawing For GCS Bridges |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0073-ST-T-2469 |  |  | Transmital Date:11/6/2023
[5 empty] | CRS No:PEDCO-CRS- BK-GCS-PEDCO-120-ST-DW-0085_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-349987 | 1402/08/30 | مدارک محاسباتی و آلبوم نقشه ها در یک ترنسمیتال ارسال می گردد
2 |  |  | 1402-2294-349987 | 1402/08/30 | با توجه به لزوم انجام طراحی بهینه مهندسی به لحاظ مالی/زمانی و از طرف دیگر عدم الزام قراردادی به استفاده همه جانبه از نقشه های استاندارد سازمان برنامه و بودجه، ادامه کار بر اساس طراحی این پیمانکار مدنظر قرار میگیرد
3 |  |  | 1402-2294-349987 | 1402/08/30 | برای دیوارهای بالی (حائل) محاسبات اراِئه گردیده است
4 |  |  | 1402-2294-349987 | 1402/08/30 | لیستوفر به آلبوم نقشه ها اضافه گردید
5 |  |  | 1402-2294-349987 | 1402/08/30 | با توجه به محدودیت موجود ( کانال رواناب سطحی ) در دوطرف جاده و محاسبات ، نیازی به پاشنه بیرونی نمی باشد
6 |  |  | 1402-2294-349987 | 1402/08/30 | آرماتور ها تا سطح میلگردهای سفره تحتانی امتداد داده شد
7 |  |  | 1402-2294-349987 | 1402/08/30 | قلاب های S به دیوارها اضافه گردید
8 |  |  | 1402-2294-349987 | 1402/08/30 | جزئیات هندریل بر اساس نشریه 292/1 اضافه گردید
9 |  |  | 1402-2294-349987 | 1402/08/30 | لوله های عبوری ترسیم گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: