## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-EL-CN-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2129 |  |  | Transmital Date: 5/21/2023
Document Title: Calculation Note For UPS System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-EL-TR-2129 |  |  | Transmital Date: 5/21/2023
[5 empty] | CRS No: NISOC-CRS- BK-GCS-PEDCO-120-EL-CN-0004_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم تأیید بار مصرفی سیستم کنترل و ابزاردقیق، مقتضی است این مدرک پس از نهایی سازی مدرک I&C Consumption Summary به روزرسانی و اصلاح گردد. |  | 1402-2294-95482 | 1402/03/11 | با توجه به نیاز به نهایی سازی سایز ترانسفورماتور و تابلوهای LV، این مدرک می بایست مورد ویرایش قرار گیرد. بر همین اساس آخرین لیست بار ابزاردقیق به عنوان رفرنس قرار گرفته و مدرک محاسباتی ارائه می گردد.
2 | تا نهایی شدن مدرک I&C از ارسال ویرایش جدید محاسبات خودداری گردد. |  | 1402-2294-95482 | 1402/03/11
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: