## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0075 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2391 |  |  | Transmital Date:9/27/2023
Document Title: Foundation Drawing For CCTV Control Room- Binak GCS |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2391 |  |  | Transmital Date:9/27/2023
[5 empty] | CRS No:PEDCO-CRS- BK-GCS-PEDCO-120-ST-DW-0075_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-310722 | 1402/08/06 | اصولا مدارک (دفترچه محاسبات و آلبوم نقشه ها) بهمراه فایل محاسباتی جهت مطالعه و بررسی و اظهار نظر برای کارفرمای محترم ارسال می گردد. مجددا لوح فشرده فایل محاسباتی بهمراه مدارک اصلاح شده بحضورتان ایفاد می گردد
2 |  |  | 1402-2294-310722 | 1402/08/06 | توسط تیم مدیریت ارسال می گردد
3 |  |  | 1402-2294-310722 | 1402/08/06 | محل مورد نظر به نقشه ها اضافه گردید
4 |  |  | 1402-2294-310722 | 1402/08/06 | دیتایل مورد نظر اضافه گردید
5 |  |  | 1402-2294-310722 | 1402/08/06 | با توجه به ارتفاع 60 سانتیمتری نیازی به میلگرد مذکور نمی باشد
6 |  |  | 1402-2294-310722 | 1402/08/06 | جدول لیستوفر در شیت 2 ارائه شده است
7 |  |  | 1402-2294-310722 | 1402/08/06 | میلگرد مورد نظر در مقطع ستون (تیپ C1) موجود می باشد
8 |  |  | 1402-2294-310722 | 1402/08/06 | سنجاقک ها اضافه گردید
9 |  |  | 1402-2294-310722 | 1402/08/06 | مطابق با بند 9-20-5-3-3-3 اصلاح گردید
10 |  |  | 1402-2294-310722 | 1402/08/06 | طول همپوشانی میلگرد ها ارائه شده است
11 |  |  | 1402-2294-310722 | 1402/08/06 | نوت شماره 6 جهت کاور بتن ارائه شده است
12 |  |  | 1402-2294-310722 | 1402/08/06 | نوت شماره 9 جهت تراکم ارائه شده است
13 |  |  | 1402-2294-310722 | 1402/08/06 | نوت شماره 10 به نقشه اضافه گردید
14 |  |  | 1402-2294-310722 | 1402/08/06 | پلیت مورد نظر در پلان سقف جانمایی و جزئیات ارائه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: